## User Stories
ID | Story Title | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | NFR | Definition of Done | Epic ID | Notes | Status
A0 | Meeting Logs | 8 | High | Administrator | Manage meeting logs | I and other users know what meetings we have had in the past | NA | A full CRUD for meeting logs | LOGS0 |  | Open
A1 | Search Logs | 5 | Low | Administrator | Search through previous meeting logs | I can find information from previous meetings more easily | Must respond relatively quickly, Accept a number of parameters | When one can search meeting logs and sort them based on keywords, date, speaker, etc. |  | Can be built incrementally. First doing keywords, then sorting by date, etc. | Open
A2 | Announce Meetings | 8 | High | Administrator | Create announcement for upcoming meetings | Users of the site know when the meeting occurs | Preferred in a Calendar format with date, time, details of meeting | A full CRUD for upcoming meetings | MEETS0 |  | Open
A3 | Create Meeting Logs | 2 | High | Administrator | Create logs of meetings | Users have a record of what the organization has done | NA | When there is a way to enter information about a meeting on the frontend and it is stored in the backend | LOGS0 |  | Open
A4 | Update Meeting Logs | 2 | High | Administrator | Update logs of meetings | Any potential mistakes for a meeting can be corrected | NA | When an administrator is able to change the details of the meeting log | LOGS0 |  | Open
A5 | Delete Meeting Logs | 2 | High | Administrator | Delete potential meeting log entries | If a log is created by mistake or is incorrect, it can be removed | Deleted logs should be recoverable in case they are mistakenly deleted | When there is a way to delete a meeting log on the frontend that affects the backend | LOGS0 |  | Open
A6 | Announce News | 3 | Medium | Administrator | Have a banner announcing upcoming meetings and news on the homepage | Users and speakers coming to the site know upcoming organization activites | NA | When there is an updatable banner with news information on the home page that can be changed by the Clients |  |  | Open
S0 | Contact Admins | 3 | High | Speaker | Contact the administrators | They can set up meetings for me to speak | Email Administrators if the message is not responded to for a while | When there is a messaging system from speaker to admin |  | Again, can use contact information from speakers as a placeholder | Open
U0 | Rate Meetings | 2 | Low | User | Rate meetings that have occurred | The organization leaders have feedback on speakers, leaders, etc. | Should probably only have rating enabled after a meeting occurs for a fixed amount of time | When users can rate (possibly review) meetings |  | May help to figure out how to generate static links to rate meetings | Open
U1 | Paying Dues | 13 | Medium | User | Pay dues to the organization through the site | The organization has revenue to engage in its operations | High security, possibly encryption | When users can pay through the site | PAY0 | The clients informed us that there are external links to pay dues. Can use those as a placeholder in case we do not finish this epic | Open
U2 | View Logs | 2 | High | User | View logs of previous meetings | I know what the organization has done in the past | NA | When logs on the backend can be viewed in the frontend | LOGS0 | Viewing logs should be in a calendar format | Open

## Tasks
ID | Task Title | Task Description | Story ID

## Epics
ID | Epic Title | Description

## NFR
ID | Title | Category | Description | Affects
1 | Color Scheme | Visual / Design | The color scheme for the app should be *** | All
2 | Understand a NFR | Understandability | Simple example for the students to understand | Some